## Gantt Chart
Practise enterprise 1 By Thomas Van Nuffel
| 2020-10-12 | 1 |  |  |  | 2020-10-12 |  |  |  | 2020-10-18 |  |  | 2020-10-19 |  |  |  | 2020-10-25 |  |  | 2020-10-26 |  |  |  | 2020-11-01 |  |  | 2020-11-02 |  |  |  | 2020-11-08 |  |  | 2020-11-09 |  |  |  | 2020-11-15 |  |  | 2020-11-16 |  |  |  | 2020-11-22 |  |  | 2020-11-23 |  |  |  | 2020-11-29 |  |  | 2020-11-30 |  |  |  | 2020-12-06 |  |  | 2020-12-07 |  |  |  | 2020-12-13 |  |  | 2020-12-14 |  |  |  | 2020-12-20
 | time axis 2020-10-12 to 2020-12-20
| Task | Start | Progress | End | time axis 2020-10-12 to 2020-12-20
Urenregistratie!A1 | Total: | 2020-10-14 | 25.32% | 2021-05-30
| Preparations | 2020-10-18 | 100% | 2020-10-20 | X
https://www.youtube.com/watch?v=un8j6QqpYa0&t=646s | Knowing how this works | 2020-10-18 | 100% | 2020-10-19 | X
| Getting a Gantt Chart | 2020-10-19 | 100% | 2020-10-20 | X
..\Theory | Theory | 2020-10-19 | 31.59% | 2020-12-01
..\Theory\XC888 | Datasheet XC888 | 2020-10-27 | 14.29% | 2020-11-22
| Sensor Research | 2020-10-19 | 70% | 2020-12-01
| Scan matrix keys + leds | 2020-11-14 | 100% | 2020-11-18 | X
| Digital and analog reading of a pin |  | 0%
| Digital to analog conversion | 2020-11-09 | 0%
| Store data on external drives |  | 0%
| Communication XC888s | 2020-11-11 | 100% | 2020-12-01 | X
| PWM |  | 0%
| MIDI |  | 0%
| Documentation | 2020-10-14 | 53.64% | 2020-11-18
..\Theory\MIDI | MIDI documentation | 2020-10-14 | 100% | 2020-11-03 | X
..\Theory\converter analog to digital\Analog to digital conversion 1.0.docx | Analog to digital conversion | 2020-11-02 | 100% | 2020-11-02 | X
| Digital to analog conversion | 2020-11-09 | 60%
| Scan matrix keys | 2020-11-15 | 80%
| Matrix for driving leds |  | 40%
| Sound | 2020-11-17 | 100% | 2020-11-18 | X
| Hearing | 2020-11-18 | 100% | 2020-11-18
| Sensors |  | 0%
| Storage management |  | 0%
| Communication XC888s |  | 0%
| Terminology | 2020-11-02 | 10%
| Schematics | 2020-11-16 | 33.33% | 2020-11-16
| The schematic of my project |  | 0%
| Scan Matrix keys | 2020-11-16 | 100% | 2020-11-16 | X
| Scan Matrix leds |  | 0%
| Place of XC888(s) and input and output |  | 0%
| To-do | 2020-11-15 | 33.33% | 2020-11-15
..\Theory\Scan Matrix | Figure out scan Matrix | 2020-11-15 | 100% | 2020-11-15 | X
| Using the buzzer of the XC888 |  | 0%
| Searching wavetables |  | 0%
| Designs and buildings | 0 | 0% | 0
| Design PCB |  | 0%
| Housing distance and laser |  | 0%
| Pedal |  | 0%
| 3D printed things | 0 | 0% | 0
| Housing distance and laser |  | 0%
| Pedal |  | 0%
| Extra | 2020-11-02 | 25% | 2020-11-22
..\Theory\converter analog to digital | Analog to digital conversion | 2020-11-02 | 100% | 2020-11-22 | X
| Analog to digital converter |  | 0%
| Input amplifier to output |  | 0%
| LED's on output |  | 0%
Practise Enterprise book | Practise Enterprise 1 book

## Registration
Practise Enterprise 1
Day | Date | Subject | What did you do ? | Time spend in minutes | Total hours | Subtotals
| Daarvoor | MIDI theory Asking Permission | documentation Sending mails | 600 | 10
Ma | 2020-10-19 | Documentation | Which messages have which parameters | 120 | 2 | 2
Di | 2020-10-20 |  |  |  | 0
Wo | 2020-10-21 |  |  |  | 0
Do | 2020-10-22 |  |  |  | 0
Vr | 2020-10-23 |  |  |  | 0
Za | 2020-10-24 |  |  |  | 0
Zo | 2020-10-25 |  |  |  | 0
Ma | 2020-10-26 |  |  |  | 0 | 1.7667
Di | 2020-10-27 |  |  |  | 0
Wo | 2020-10-28 | To do | Search for components online | 46 | 0.76667
Do | 2020-10-29 |  |  |  | 0
Vr | 2020-10-30 | Excel | Gant chart aangevuld | 60 | 1
Za | 2020-10-31 |  |  |  | 0
Zo | 2020-11-01 |  |  |  | 0
Ma | 2020-11-02 | Theory | Analog to digital conversion | 120 | 2 | 2.25
Di | 2020-11-03 | Documentation | Documentation ready on drive | 15 | 0.25
Wo | 2020-11-04 |  |  |  | 0
Do | 2020-11-05 |  |  |  | 0
Vr | 2020-11-06 |  |  |  | 0
Za | 2020-11-07 |  |  |  | 0
Zo | 2020-11-08 |  |  |  | 0
Ma | 2020-11-09 |  |  |  | 0 | 4.5
Di | 2020-11-10 |  |  | 30 | 0.5
Wo | 2020-11-11 |  |  |  | 0
Do | 2020-11-12 |  |  |  | 0
Vr | 2020-11-13 |  |  |  | 0
Za | 2020-11-14 |  |  |  | 0
Zo | 2020-11-15 | Schematic + Theory | Matrices keys + leds on tinkercad XC888 datasheet | 240 | 4
Ma | 2020-11-16 | Schematic | Scan matrix of keyboard on multisim | 60 | 1 | 4
Di | 2020-11-17 | Excel + documentation | Gantt Chart What is sound ? | 180 | 3
Wo | 2020-11-18 |  |  |  | 0
Do | 2020-11-19 |  |  |  | 0
Vr | 2020-11-20 |  |  |  | 0
Za | 2020-11-21 |  |  |  | 0
Zo | 2020-11-22 |  |  |  | 0
Ma | 2020-11-23 |  |  |  | 0 | 0
Di | 2020-11-24 |  |  |  | 0
Wo | 2020-11-25 |  |  |  | 0
Do | 2020-11-26 |  |  |  | 0
Vr | 2020-11-27 |  |  |  | 0
Za | 2020-11-28 |  |  |  | 0
Zo | 2020-11-29 |  |  |  | 0
Ma | 2020-11-30 |  |  |  | 0 | 0
Di | 2020-12-01 |  |  |  | 0
Wo | 2020-12-02 |  |  |  | 0
Do | 2020-12-03 |  |  |  | 0
Vr | 2020-12-04 |  |  |  | 0
Za | 2020-12-05 |  |  |  | 0
Zo | 2020-12-06 |  |  |  | 0
Ma | 2020-12-07 |  |  |  | 0 | 0
Di | 2020-12-08 |  |  |  | 0
Wo | 2020-12-09 |  |  |  | 0
Do | 2020-12-10 |  |  |  | 0
Vr | 2020-12-11 |  |  |  | 0
Za | 2020-12-12 |  |  |  | 0
Zo | 2020-12-13 |  |  |  | 0
Ma | 2020-12-14 |  |  |  | 0 | 0
Di | 2020-12-15 |  |  |  | 0
Wo | 2020-12-16 |  |  |  | 0
Do | 2020-12-17 |  |  |  | 0
Vr | 2020-12-18 |  |  |  | 0
Za | 2020-12-19 |  |  |  | 0
Zo | 2020-12-20 |  |  |  | 0
Ma | 2020-12-21 |  |  |  | 0 | 0
Di | 2020-12-22 |  |  |  | 0
Wo | 2020-12-23 |  |  |  | 0
Do | 2020-12-24 |  |  |  | 0
Vr | 2020-12-25 |  |  |  | 0
Za | 2020-12-26 |  |  |  | 0
Zo | 2020-12-27 |  |  |  | 0
Ma | 2020-12-28 |  |  |  | 0 | 0
Di | 2020-12-29 |  |  |  | 0
Wo | 2020-12-30 |  |  |  | 0
Do | 2020-12-31 |  |  |  | 0
Vr | 2021-01-01 |  |  |  | 0
Za | 2021-01-02 |  |  |  | 0
Zo | 2021-01-03 |  |  |  | 0
Ma | 2021-01-04 |  |  |  | 0 | 0
Di | 2021-01-05 |  |  |  | 0
Wo | 2021-01-06 |  |  |  | 0
Do | 2021-01-07 |  |  |  | 0
Vr | 2021-01-08 |  |  |  | 0
Za | 2021-01-09 |  |  |  | 0
Zo | 2021-01-10 |  |  |  | 0
Ma | 2021-01-11 |  |  |  | 0 | 0
Di | 2021-01-12 |  |  |  | 0
Wo | 2021-01-13 |  |  |  | 0
Do | 2021-01-14 |  |  |  | 0
Vr | 2021-01-15 |  |  |  | 0
Za | 2021-01-16 |  |  |  | 0
Zo | 2021-01-17 |  |  |  | 0
Ma | 2021-01-18 |  |  |  | 0 | 0
Di | 2021-01-19 |  |  |  | 0
Wo | 2021-01-20 |  |  |  | 0
Do | 2021-01-21 |  |  |  | 0
Vr | 2021-01-22 |  |  |  | 0
Za | 2021-01-23 |  |  |  | 0
Zo | 2021-01-24 |  |  |  | 0
Ma | 2021-01-25 |  |  |  | 0 | 0
Di | 2021-01-26 |  |  |  | 0
Wo | 2021-01-27 |  |  |  | 0
Do | 2021-01-28 |  |  |  | 0
Vr | 2021-01-29 |  |  |  | 0
Za | 2021-01-30 |  |  |  | 0
Zo | 2021-01-31 |  |  |  | 0
Ma | 2021-02-01 |  |  |  | 0 | 0
Di | 2021-02-02 |  |  |  | 0
Wo | 2021-02-03 |  |  |  | 0
Do | 2021-02-04 |  |  |  | 0
Vr | 2021-02-05 |  |  |  | 0
Za | 2021-02-06 |  |  |  | 0
Zo | 2021-02-07 |  |  |  | 0
Ma | 2021-02-08 |  |  |  | 0 | 0
Di | 2021-02-09 |  |  |  | 0
Wo | 2021-02-10 |  |  |  | 0
Do | 2021-02-11 |  |  |  | 0
Vr | 2021-02-12 |  |  |  | 0
Za | 2021-02-13 |  |  |  | 0
Zo | 2021-02-14 |  |  |  | 0
Ma | 2021-02-15 |  |  |  | 0 | 0
Di | 2021-02-16 |  |  |  | 0
Wo | 2021-02-17 |  |  |  | 0
Do | 2021-02-18 |  |  |  | 0
Vr | 2021-02-19 |  |  |  | 0
Za | 2021-02-20 |  |  |  | 0
Zo | 2021-02-21 |  |  |  | 0
Ma | 2021-02-22 |  |  |  | 0 | 0
Di | 2021-02-23 |  |  |  | 0
Wo | 2021-02-24 |  |  |  | 0
Do | 2021-02-25 |  |  |  | 0
Vr | 2021-02-26 |  |  |  | 0
Za | 2021-02-27 |  |  |  | 0
Zo | 2021-02-28 |  |  |  | 0
Ma | 2021-03-01 |  |  |  | 0 | 0
Di | 2021-03-02 |  |  |  | 0
Wo | 2021-03-03 |  |  |  | 0
Do | 2021-03-04 |  |  |  | 0
Vr | 2021-03-05 |  |  |  | 0
Za | 2021-03-06 |  |  |  | 0
Zo | 2021-03-07 |  |  |  | 0
Ma | 2021-03-08 |  |  |  | 0 | 0
Di | 2021-03-09 |  |  |  | 0
Wo | 2021-03-10 |  |  |  | 0
Do | 2021-03-11 |  |  |  | 0
Vr | 2021-03-12 |  |  |  | 0
Za | 2021-03-13 |  |  |  | 0
Zo | 2021-03-14 |  |  |  | 0
Ma | 2021-03-15 |  |  |  | 0 | 0
Di | 2021-03-16 |  |  |  | 0
Wo | 2021-03-17 |  |  |  | 0
Do | 2021-03-18 |  |  |  | 0
Vr | 2021-03-19 |  |  |  | 0
Za | 2021-03-20 |  |  |  | 0
Zo | 2021-03-21 |  |  |  | 0
Ma | 2021-03-22 |  |  |  | 0 | 0
Di | 2021-03-23 |  |  |  | 0
Wo | 2021-03-24 |  |  |  | 0
Do | 2021-03-25 |  |  |  | 0
Vr | 2021-03-26 |  |  |  | 0
Za | 2021-03-27 |  |  |  | 0
Zo | 2021-03-28 |  |  |  | 0
Ma | 2021-03-29 |  |  |  | 0 | 0
Di | 2021-03-30 |  |  |  | 0
Wo | 2021-03-31 |  |  |  | 0
Do | 2021-04-01 |  |  |  | 0
Vr | 2021-04-02 |  |  |  | 0
Za | 2021-04-03 |  |  |  | 0
Zo | 2021-04-04 |  |  |  | 0
Ma | 2021-04-05 |  |  |  | 0 | 0
Di | 2021-04-06 |  |  |  | 0
Wo | 2021-04-07 |  |  |  | 0
Do | 2021-04-08 |  |  |  | 0
Vr | 2021-04-09 |  |  |  | 0
Za | 2021-04-10 |  |  |  | 0
Zo | 2021-04-11 |  |  |  | 0
Ma | 2021-04-12 |  |  |  | 0 | 0
Di | 2021-04-13 |  |  |  | 0
Wo | 2021-04-14 |  |  |  | 0
Do | 2021-04-15 |  |  |  | 0
Vr | 2021-04-16 |  |  |  | 0
Za | 2021-04-17 |  |  |  | 0
Zo | 2021-04-18 |  |  |  | 0
Ma | 2021-04-19 |  |  |  | 0 | 0
Di | 2021-04-20 |  |  |  | 0
Wo | 2021-04-21 |  |  |  | 0
Do | 2021-04-22 |  |  |  | 0
Vr | 2021-04-23 |  |  |  | 0
Za | 2021-04-24 |  |  |  | 0
Zo | 2021-04-25 |  |  |  | 0
Ma | 2021-04-26 |  |  |  | 0 | 0
Di | 2021-04-27 |  |  |  | 0
Wo | 2021-04-28 |  |  |  | 0
Do | 2021-04-29 |  |  |  | 0
Vr | 2021-04-30 |  |  |  | 0
Za | 2021-05-01 |  |  |  | 0
Zo | 2021-05-02 |  |  |  | 0
Ma | 2021-05-03 |  |  |  | 0 | 0
Di | 2021-05-04 |  |  |  | 0
Wo | 2021-05-05 |  |  |  | 0
Do | 2021-05-06 |  |  |  | 0
Vr | 2021-05-07 |  |  |  | 0
Za | 2021-05-08 |  |  |  | 0
Zo | 2021-05-09 |  |  |  | 0
Ma | 2021-05-10 |  |  |  | 0 | 0
Di | 2021-05-11 |  |  |  | 0
Wo | 2021-05-12 |  |  |  | 0
Do | 2021-05-13 |  |  |  | 0
Vr | 2021-05-14 |  |  |  | 0
Za | 2021-05-15 |  |  |  | 0
Zo | 2021-05-16 |  |  |  | 0
Ma | 2021-05-17 |  |  |  | 0 | 0
Di | 2021-05-18 |  |  |  | 0
Wo | 2021-05-19 |  |  |  | 0
Do | 2021-05-20 |  |  |  | 0
Vr | 2021-05-21 |  |  |  | 0
Za | 2021-05-22 |  |  |  | 0
Zo | 2021-05-23 |  |  |  | 0
Ma | 2021-05-24 |  |  |  | 0 | 0
Di | 2021-05-25 |  |  |  | 0
Wo | 2021-05-26 |  |  |  | 0
Do | 2021-05-27 |  |  |  | 0
Vr | 2021-05-28 |  |  |  | 0
Za | 2021-05-29 |  |  |  | 0
Zo | 2021-05-30 |  |  |  | 0
Ma | 2021-05-31 |  |  |  | 0 | 0
Di | 2021-06-01 |  |  |  | 0
Wo | 2021-06-02 |  |  |  | 0
Do | 2021-06-03 |  |  |  | 0
Vr | 2021-06-04 |  |  |  | 0
Za | 2021-06-05 |  |  |  | 0
Zo | 2021-06-06 |  |  |  | 0
Ma | 2021-06-07 |  |  |  | 0 | 0
Di | 2021-06-08 |  |  |  | 0
Wo | 2021-06-09 |  |  |  | 0
Do | 2021-06-10 |  |  |  | 0
Vr | 2021-06-11 |  |  |  | 0
Za | 2021-06-12 |  |  |  | 0
Zo | 2021-06-13 |  |  |  | 0
Ma | 2021-06-14 |  |  |  | 0
Di | 2021-06-15 |  |  |  | 0
Wo | 2021-06-16 |  |  |  | 0
Do | 2021-06-17 |  |  |  | 0
Vr | 2021-06-18 |  |  |  | 0
[5 empty] | 24.5167 | 13.62%

## Database components
Component | Group | Name | Price | Units | Price/ Unit | Datasheet | Website
HC-04SR | Sensors | Distance sensor | 1.69 | 1 | 1.69
Laser diode 650nm 5mW LoC | Cool | Laser | 0.93 | 1 | 0.93 | No
MAX5550ETE+ | Converters | DAC | 3.69 | 1 | 3.69 | ok | t.ly/6xlF
MAX11610 series | Converters | ADC's | 4 | 1 | 4

## Costs
Material | Purchased quantity | Total Price | Used | Price | Not used | Price2 | Price/ Unit | Group
HC-04SR | 5 | 8.45 |  | 0 | 5 | 8.45 | 1.69 | Sensors
Laser diode 650nm 5mW LoC | 4 | 3.72 |  | 0 |  | 0 | 0.93 | Cool
MAX5550ETE+ |  | 0 |  | 0 |  | 0 | 3.69 | Converters
MAX11610 series |  | 0 |  | 0 |  | 0 | 4 | Converters

## Product cost
Material | Used quantity | Price/ Unit | Total Price | Used | Group
HC-04SR | 1 | 1.69 | 1.69 |  | Sensors
Laser diode 650nm 5mW LoC |  | 0.93 | 0 |  | Cool
MAX5550ETE+ |  | 3.69 | 0 |  | Converters
MAX11610 series |  | 4 | 0 |  | Converters

## Production Cost
Material | quantity | Price/ Unit | Total Price | Used | Group
HC-04SR |  | 1.69 | 0 |  | Sensors
|  | #N/A | #N/A |  | #N/A
|  | #N/A | #N/A |  | #N/A
|  | #N/A | #N/A |  | #N/A

## Scan Matrix Keys
w1 | w2 | Note | Place Piano | w1 | w2 | Note | Place Piano
1 | 15 | DO1 | 1 | 5 | 15 | FAk4 | 8
1 | 14 | DOk1 |  | 5 | 14 | SOL4
1 | 13 | RE1 |  | 5 | 13 | SOLk4
1 | 12 | REk1 |  | 5 | 12 | LA4
1 | 11 | MI1 |  | 5 | 11 | LAk4
1 | 10 | FA1 |  | 5 | 10 | SI4
2 | 15 | FAk1 | 2 | 6 | 15 | DO4 | 7
2 | 14 | SOL1 |  | 6 | 14 | DOk4
2 | 13 | SOLk1 |  | 6 | 13 | RE4
2 | 12 | LA1 |  | 6 | 12 | REk4
2 | 11 | LAk1 |  | 6 | 11 | MI4
2 | 10 | SI1 |  | 6 | 10 | FA4
3 | 15 | FAk2 | 4 | 7 | 15 | FAk3 | 6
3 | 14 | SOL2 |  | 7 | 14 | SOL3
3 | 13 | SOLk2 |  | 7 | 13 | SOLk3
3 | 12 | LA2 |  | 7 | 12 | LA3
3 | 11 | LAk2 |  | 7 | 11 | LAk3
3 | 10 | SI2 |  | 7 | 10 | SI3
4 | 15 | DO5 | 9 | 8 | 15 | DO3 | 5
4 | 14 | / |  | 8 | 14 | DOk3
4 | 13 | / |  | 8 | 13 | RE3
4 | 12 | / |  | 8 | 12 | REk3
4 | 11 | / |  | 8 | 11 | MI3
4 | 10 | / |  | 8 | 10 | FA3
|  |  |  | 9 | 15 | DO2 | 3
|  |  |  | 9 | 14 | DOk2
|  |  |  | 9 | 13 | RE2
|  |  |  | 9 | 12 | REk2
|  |  |  | 9 | 11 | MI2
|  |  |  | 9 | 10 | FA2

## Proposal Orders
Group | Component | Price/Unit | Pieces | Verzending | Total Price | Website
Sensors | HC-SR04 | 3.65 | 2 | 6.95 | 14.25 | shorturl.at/bhIM8
Sensors | HC-SR04 | 1.1 | 2 | 2.17 | 4.37
Sensors | HC-SR04 x2 | 2.54 | 1 | 2.17 | 4.71
Sliders | RS60112-LIN100K | 3.13 | 8 | 6.95 | 31.99
Light | Laser diode | 0.93 | 2 | 4.09 | 5.95
Microcontroller | NXP LPC1114FBD48/302 | 3.12 | 1 | 4.95 | 8.07 | shorturl.at/dnsxA